## Requirement Breakdown - EN
| Features | [21 empty] | Timeline
| Epic | Story | User Stories | Acceptance criteria |  |  | Corner Cases: | Task | Sub-task | Request Date | PIC |  | Priority | Estimation | Status | Completion Date | Commit ID | Note | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
|  |  |  | Admin | User experience | System Verification
1 | Ticket Shop | In-App Purchase | Users can view the list of available packages in the Ticket Shop, so they can choose the package they want to buy. | 1. List of item packages must be clearly displayed with: - Illustration photo of the item package. - Description of the item package: How many Tickets (Spins) and how many Coins are included - Price of the item package (displayed in Telegram Star units). 2. Users can touch the item package to see more detailed information, including: - Benefits that the package provides: How many Tickets (Spins) and how many Coins are included - "Buy" button to make a redirect to Telegram's payment portal. (Catizen for ref) |  |  | 1. User does not have enough Telegram Stars: Displays a screen with instructions on how to top up more Stars. 2. Network error: Notify error and keep transaction status on hold. 3. If the user leaves the app during the payment process: Keep the transaction status pending so that when the user returns, he or she can continue from the previous step. | Detailed analysis | Provide documentation and create related documents |  | My - BA |  | 1
[8 empty] | Payment API integration with Telegram Star. | Send a payment request and receive a response from the Telegram system |  | Hùng - FE
[8 empty] | Ticket management | Add Ticket to user's Ticket wallet after purchase |  | Hoàng - BE
|  |  | Users can purchase item packages from the store using Telegram Star, to be able to use tickets | 3. When a user chooses to purchase an item package, a confirmation dialog box with the following information must be displayed: - Item package name. - Buy button displays the amount of Telegram Star needed to purchase the package - button X to cancel popup. 4. After the user presses the Buy Button: - Display Telegram's ""Confirm Your Purchase"" popup - Check if the user balance has enough Telegram Star or not. If not enough, display to Telegram's Telegram Star purchase page. - If the balance is sufficient, deduct the corresponding number of Telegram Stars and the system displays a Successfully Purchased Popup with information about the package the User received. 5. After turning off the popup, the amount of Tickets is immediately added to the user's Ticket wallet (shown above Spin Limit). The user's Coin count increases. The screen is still displayed at the Ticket Shop |  |  |  | Manage transaction history | - Save transaction information (time, item name, number of Telegram Stars, status). - Create an API so the frontend can query transaction history |  | Hoàng - BE
[8 empty] | Build the Ticket Shop interface | Displays a list of item packages, including name, description, and price |  | Hue - Des | Hùng - FE
[9 empty] | Build UI for payment confirmation process. |  | Hue - Des | Hùng - FE
2 |  | Onchain Daily by Ton Space | Users connect their wallets to the system through TON Space | 1. Users can see the wallet connection option in the application interface. 2. Upon selecting the connection option, the user will be asked to log in to the TON wallet and authorize. 3. After successful connection, the system will display wallet address information and current balance. 4. If the connection fails, an error message will appear (e.g. “Unable to connect to wallet, please try again.”) |  |  | - Network connection lost: If the player chooses to Check-in via the TON network and loses network connection, the system will notify an error and ask to try again later. - TON transaction fails: In case a TON Smart Contract transaction fails (due to contract error, insufficient funds, etc.), the system will report an error and no reward will be given. - Check TON wallet: If the player does not have a TON wallet or has not linked a wallet, the system will request to link a TON wallet before making a purchase using the TON network. | TON Wallet API integration |  |  |  | Hùng - FE | 1
|  |  | The system checks the user's wallet balance before making a transaction. | 1. When the user clicks on Onchain Check-in Package, the system will open the Ton Space wallet popup and check the wallet balance. 2. If the balance is not enough, Popup wallet displays "Insufficent balance" and suggests Deposit Ton Space to continue the transaction. 3. If the balance is sufficient, the system will allow the user to proceed with the transaction. |  |  |  | Check wallet information | - Check wallet balance |  |  | Hoàng - BE
|  |  | Users make onchain transactions through the connected wallet to receive daily reward Tickets. | 1. Users can only make a successful transaction once per day. 2. After a successful transaction, the user will receive a notification about the completed transaction. 3. Users will receive 5 Tickets in the Ticket wallet after a successful transaction. 4. If the transaction fails (due to network or blockchain error), the user will not receive the ticket and the system will display a detailed error message. |  |  |  | Deploy Smart Contract | - Create transaction SC for users
Handle daily transaction limits
|  |  | Limit the user's trading frequency to avoid making multiple transactions per day. | 1. Users can only make onchain transactions once per day. 2. After the daily transaction limit is reached, the system will lock this function until the new date starts |  |  |  | Notification of reward after successful transaction |  |  |  | Hùng - FE
3 |  | Login | Admins can log in to the Admin Portal system to access functions based on their permissions. | 1. Admin has an account to log into the Admin system (username + password) 2. Super Admin has the right to create additional Admin user accounts and assign rights to two types of roles. - Admin 1 (Event manager): has the right to set parameters and add, edit, read and delete events - Admin 2 (Data viewer): only has the right to search data and read & check set events. 3. If login fails, the system displays the correct error message (e.g. ""Incorrect username or password"). |  |  | 1. Incorrect password multiple times: - If you enter an incorrect email, it still shows that the account does not exist. Notification content: "Your account is not found" - If you enter the correct email but the wrong password more than 5 times, your account will be inactive. "You have logged in incorrectly. If you log in incorrectly more than 5 times, your account will be inactivated." - The fifth time you enter it incorrectly, it will notify you that: "You have logged in incorrectly 5 times, your account will be inactivated" - After 5 incorrect entries and still enter again (whether you enter correctly or incorrectly): "Your account has been inactivated. Contact your administrator to activate the account" => If admin user's account is inactivated, Super Admin has to update the status for this account on User Management to activate the account. 2. Admin has not been authorized: If the Admin has not been assigned valid rights, the system will display a message (for example: ""You do not have access rights""). | Design and implement Admin authentication system. |  |  |  | Huy - BE | 2
[8 empty] | Store role information in the database. |  |  |  | Huy - BE
[8 empty] | Implement account locking function after multiple failed login attempts. |  |  |  | Huy - BE
Huy - BE
|  | Role-Based Access Control | Super Admin can manage the rights and roles of admin users. | 1. Super Admin can add, edit (role), and delete admin users. 2. Super Admin can assign the event_manager or data_viewer role to admin users. 3. Super Admin has the right to reset password, activate locked accounts of Admin users. 4. Super Admin cannot assign admin rights to himself (avoid the error of changing roles yourself). 5. Every time changing permissions, the system will send a confirmation message. |  |  | 1. Change role for Super Admin: Do not allow Super Admin to change his role or downgrade. 2. Add duplicate admin user: Do not allow adding an admin user that already exists in the system. | Design an interface that only views and handles access rights. |  |  | Hue - Des | Hùng - FE
[8 empty] | Create an endpoint to manage admin user rights and roles (CRUD). |  |  | Huy - BE
[8 empty] | Process logic to distinguish the rights of Super Admin, Event Manager and Data viewer. |  |  | Huy - BE
|  | View database | Admin can view data from tables in the database and download it as CSV format file. | 1. Admin can view data from the tables: User, Friend, User To Boost, User To Earn, User To Invest, Wheel History, and Event Log. 2. Admin can use filters to search data: - Enter the desired time period (for example: 2024-01-30 to 2024-01-30). - Use the search field with criteria such as: “username”, “name”, “ID”, “wallet address” - Choose to sort in ascending or descending order of one or more columns in the table 3. Admin click on the "Download CSV" button to download the CSV file containing the searched data. - export file will export according to the filter and current page 4. Admin cannot have the right to add, edit, or delete data records in tables. Only data can be viewed and downloaded |  |  | - Unable to connect to the database: Admin lost network connection, database error,... causing admin to not be able to query the table, the system reported an error and asked to try again later - Unable to download table: Admin lost network connection, database error,... causing admin unable to query table, system reported error and asked to try again later | Create UI | - Create display UI for tables displayed in navigator |  | Hue - Des | Hùng - FE
[8 empty] | Create an API to get data and handle requests from the frontend | Create an API to get data from tables in the database |  | Huy - BE
[8 empty] | Optimize the API to support pagination when there is a lot of data. |  |  | Huy - BE
[8 empty] | Process logic that filters data based on provided criteria (e.g. time, user). |  |  | Huy - BE
[8 empty] | Set up BE to Query db | - Set up BE to connect tables to parts of the admin UI |  | Huy - BE
[8 empty] | Create a function to download tables as csv | - Create load function - Facilitates filtering for downloads |  | Huy - BE
| Admin | Daily Quest main screen | Admin can view fixed quests and recently created quests | 1. Display Quest 1-2-3-4 as fixed quests in the app, including: - Daily Check-in reward - Spin Apprentice - Spin Master - Say GM on our TG 2. Except for the fixed 1-2-3-4 quests, the following quests will be displayed according to the most recent creation time
|  | Out-link quest | Admin can create new quests | 1. Admin can navigate to Outlink Quest management page and see the button labeled ""Add Quest"" 2. When Admin clicks ""+ Add New Quest"", Admin will enter the fields displayed in the Popup, according to the form including: - Quest name * (text field) - Quest link * (URL field) - Reward coins * (number field) - Start time * (admin can only choose current or future date, cannot choose past date. If admin chooses current date, Quest will be activated immediately after Save) - Quest end time * (default quest end time is 23:59) - Image (uploaded file) * Fields marked with * are required fields | - Users can view activated tasks from the mini-app interface - Users can access external links through the Action button in the quest - Users can see the list of outlink quest | 1. The admin must fill in all required fields and upon submission, the system will: - Validate the fields (e.g. ensure the Quest Link is a valid URL, Time set is in the future). - Save the quest details to the backend database. - Display a success message if the quest was successfully added. 2. After successfully adding the quest, the newly created quest will appear in the recent quests list, including all the information provided, including a Status column 3. The status column will automatically update according to the time set for the quest (Activated/Pending) so that the admin can easily track the quests - Quests that have expired will be displayed in the Closed Quest section | 1. Admin does not fill in all information (for example: missing link or reward) → Displays an error message and does not allow saving the task. 2. If Admin tries to delete an active task, display a warning before deleting. 3. Cases where Admin must self-control - The external link is corrupted, causing users to not navigate to the correct link 4. The system needs to control cases - Users are not redirected out - Admin cannot create tasks - Admin has created the task but it is not displayed in the mini app | Design a database model for Outlink Quests. | Tạo bảng với các trường như Quest ID, Tên nhiệm vụ, Link, Phần thưởng, Trạng thái, v.v. |  | Designer | Tuấn - FE
[8 empty] | Create an API endpoint to handle requests to add new tasks (POST requests). | - Thực hiện validation để kiểm tra các trường bắt buộc (Tên Nhiệm Vụ, Link, Phần Thưởng, v.v.). - Xử lý phản hồi API thành công hoặc thất bại. |  | Huy - BE
[8 empty] | Make sure only Event Manager or Super Admin has permission to add new tasks. | Xác thực quyền truy cập của user. |  | Huy - BE
[8 empty] | Create UI input form to add new tasks. | - Thiết kế các trường nhập liệu - Xác thực dữ liệu đầu vào (ví dụ: kiểm tra link có hợp lệ không). |  | Designer | Tuấn - FE
[8 empty] | Backend API integration | Xử lý việc gửi biểu mẫu và gửi dữ liệu đến BE thông qua yêu cầu POST. |  | Tuấn - FE
[8 empty] | Update the Outlink Tasks list immediately after adding a new task | Làm mới danh sách nhiệm vụ được hiển thị trên giao diện người dùng mà không yêu cầu tải lại trang. |  | Tuấn - FE
|  |  | Admin can delete Outlink Quest when not activated | 1. Admin can click on the "Delete" icon next to any task in the recent task list. - Admin can only delete Pending tasks. Activated tasks and tasks with user interaction taking place on the mini-app cannot be deleted. 2. When Admin clicks “Delete”, the system will display a confirmation message asking “Are you sure you want to delete this task?” |  | 3. If Admin clicks confirm delete, the system will: - Delete the task from the database. - Immediately update FE to reflect the deletion of the task from the list. 4. If Admin clicks "cancel", the task remains unchanged and the deletion process will be canceled |  | Create an API endpoint to handle DELETE requests. | Check validation and see if the task exists in the database. |  | Huy - BE
[8 empty] | Implement error handling when a task cannot be deleted (e.g. invalid ID, task in use). | Return appropriate error messages when the deletion fails. |  | Huy - BE
[8 empty] | Ensure that only Event Managers or Super Admins with permission can delete tasks. | Authenticate user access. |  | Huy - BE
[8 empty] | Create a "Delete" button next to each task in the list. | Add a confirmation modal before deleting the task (e.g. "Are you sure you want to delete?") |  | Designer | Tuấn - FE
[8 empty] | Connect the delete button to the task deletion API. | Send a DELETE request to the backend with the task ID and handle success/failure. |  | Tuấn - FE
[8 empty] | Delete tasks from the UI list immediately after successful deletion. | Ensure smooth UI transitions without reloading the page. |  | Tuấn - FE
|  | Main Banner | Admin can enable/disable banners and banner settings | 1. When enabling Banner, the admin will have to install a new pair of banners by entering the information fields in the Popup to create a new banner: - Admin enters title name 1 * for the banner (required). + If the admin wants the banner to navigate to specific function screens such as the Earn and Ticket Shop screens (optional), click combo box next to title field to select a specific target screen. + If the admin only wants to display the banner in plain text, just enter the title without selecting from the combo box. + Title limited to 30 characters - Admin enters title name 2 for the banner (required): similar to Tilte 1 - Admin can specify the time the banner starts and ends. When the time ends, the banner will automatically disappear from the user interface. 2. Admin can turn off the Banner at any time. Before confirming turning off the banner, the system displays a pop up confirming turning off the banner. - When the admin confirms turning off the banner, the installed banners will be disabled (even if the banner has not expired according to the settings) 3. When turning the banner back on, the admin needs to redo the Banner settings from the beginning. 4. - Banner start time can be calculated from the time of installation or in the future, the start time cannot be selected in the past. - The banner end time must be in the future. |  | - When turning on banners: Banners will be displayed to users according to settings (navigation tabs or just displaying text). - When turning off the banner: The banner will disappear from the user's home screen immediately.
Invest Quest
Tap Quest
In-app purchase
|  | Coupon System | Admin can create new Coupon | 1. Admin can create Code (6 alphanumeric characters). 2. Admin can set the reward amount for the code (number of coins) 3. Admin can set the limit of the number of code uses 4. Admin can set the start time and end time for each code 5. Each code can only be used within the specified time and expires after that. 6. The registered code must be unique and not duplicate previously generated codes |  | - If the admin enters missing information, the system will notify an error asking to enter enough information - The generated Coupon code must be saved in the system and displayed in the Coupon list.. |  | Build Coupon UI on Admin Portal | Design a form to enter the code you want to enter. |  | Designer | Tuấn - FE |  | 4
[9 empty] | Create a Register button to add the Coupon code to the system. |  | Tuấn - FE
[9 empty] | Display a list of created Coupon codes with their status. |  | Tuấn - FE
|  |  | Admin can view the list of previously created Coupon codes | - Admin can view the list of Coupon codes that have been created, including information: code, reward, validity period, and status (pending/valid/invalid/expired - due to the time period). - There is a function to search for Coupon codes by keyword (code). - List of codes displayed in chronological order from new to old. |  |  |  | Backend processing for creating/deleting Coupon codes | Build API for Coupon Code Generation. |  | Hoàng - BE |  |  | 3
| Admin | [7 empty] | Build API for Coupon Code Deletion |  | Hoàng - FE
|  |  | Admin can invalidate the valid codes | Admin can change the status of valid code to "invalid" even if the validity period is still remaining - The system will display a confirmation message before invalidating the code. - Once invalidated, the code cannot be used by players
|  |  | Admin can view the player's code usage history | Admin can see how many users have used each code by clicking history icon in the record of that code. - When admin click the history icon, it will navigate to the Claim History screen where display a table including: No./ UserID/ User name/ Claimed At/ Coin/ Ticket |  |  |  | Create a database to store information about players who have used Coupon codes |  |  | Hoàng - FE |  |  | 3
[8 empty] | Build an API to get a list of players who have received rewards. |  |  | Hoàng - FE |  |  | 3
|  |  | Admin can delete expired Coupon codes or registered codes | - Admin can select Coupon code and delete it from the system. (it means the history of that code will be deleted as well) - The system will display a confirmation message before deleting the code. - Once deleted, the code will no longer be displayed in the list and cannot be used by players. |  |  |  | Create an API to handle verification of user input code | Create endpoint to verify code from user. |  | Hoàng - FE |  |  | 2
[8 empty] | Create logic to verify and award rewards after entering the correct code | Check code, award mission points. |  | Hoàng - FE |  |  | 2
| On App | Coupon System | Users can enter coupon code and receive reward | Reward: - If the code is valid, the user receives the reward that the admin has registered. - A code can be used by many users, but each user can only enter the same code once (meaning if you have entered this code to receive a reward, you will not receive the reward from this code anymore, entering another code will still receive the reward) |  | Code format: - Code must consist of 6 alphanumeric characters (e.g. A1B2C3). - Code entry is case-insensitive. - Special characters are not allowed to reduce data entry errors. | 1. Invalid code: If the user enters a non-existent code, the system will display the message: "Invalid code." 2. Expired code: If the code has expired (according to the time admin set), the user will receive the message: "Code has expired." 3. Maximum number of attempts: After 5 incorrect entries, the user will be locked for 3 hours and receive the message: "Maximum number of attempts reached." 4. Multiple code entries: Users cannot receive rewards multiple times for the same coupon code. The user will receive the message: "The code has been used." 5. Usage limit: If users enter the code that has reached it usage limit, the user will receive the message: "The code has reached its usage limit" 6. Invalid code: If users enter the invalid code, they will receice the message: "The code was invalid" | Generate Coupon Code | - Create an API to generate a 6-character alphanumeric code. - Set the validity period (according to the time admin set) and configure the number of uses. - Validate the code format and make it case-insensitive. |  | Hoàng - BE |  |  | 3
[8 empty] | Validate Code and Handle Errors | - Check code in DB - Call backend API to validate coupon code - Set logic to handle expired code and limit number of attempts - Block user after 5 wrong entries for 3 hours. - Return error message for invalid or expired code |  | Hoàng - BE |  |  | 3
|  |  |  | Rules of use: - Each user can enter the code up to 5 times before being locked for 3 hours if the entry limit is exceeded - The code is valid according to the time Admin configure - The number of users who can use the code depends on the limit number that the admin has set from the admin portal (if any) |  | Code Validation: - The system must validate the code based on pre-configured rules (code expiration, usage limits...). - The system displays a specific error message for some corner cases. |  | Distribute Rewards | - Create logic to distribute rewards (coins or tickets) when code is valid - Ensure that rewards are only given once per user per code. |  | Hoàng - BE |  |  | 2
[8 empty] | Notification System | Integrate notification system to notify user when code is entered successfully or with error. |  | Tuấn - FE |  |  | 1
[8 empty] | Design Coupon Code Input IU | - Design the "Enter Secret Code" input box on the Settings page - Add a "Receive" button |  | Designer | Tuấn - FE |  | 1
[6 empty] | Notification: - The system sends a confirmation message when the code is entered successfully. |  | Display Success Message | Display a confirmation message when the user enters the code successfully |  | Tuấn - FE |  |  | 1
[8 empty] | Testing Dev Environment |  |  | My - BA |  |  | 1
[8 empty] | Deploy to the production and test |  |  | Hoàng - BE |  |  | 1
|  | AdsGram Integration | Users can view ads from the Ticket Shop and Earn screens. | - User enters Ticket Shop screen and selects package with "Watch Ads" button. After watching the ad, the successful reward popup appears - User enters Earn screen and selects watch ad task. After watching the ad, the successful reward popup appears |  | - Users will be able to claim these every 3 hour - If the user attempts to claim again before the time is up, a pop-up displaying the remaining time will appear |  | Design Ads display UI on Ticket Shop and Earn. | FE build UI on the app |  | Designer | Hoàng - FE |  | 2
[8 empty] | Ads provider integration (AdsGram) | Research & SDK Integration |  | Hoàng - BE |  |  | 2
[9 empty] | Installation & Configuration |  |  |  |  | 2
[9 empty] | Setting up a Sandbox Environment |  |  |  |  | 2
[8 empty] | Place Ads in the App interface |  |  | Hoàng - BE |  |  | 2
[8 empty] | Integrate reward system | [5 empty] | 3
[8 empty] | Crate logic to claim reward | [5 empty] | 3
[8 empty] | Testing Dev Environment |  |  | My - BA |  |  | 1
[8 empty] | Deploy to the production and test |  |  | Hoàng - BE |  |  | 1
|  | Aeon Integration | Users can purchase packages in Ticket Shop with cryptocurrencies through the Aeon payment gateway | 1. Players choose Aeon icon package to pay via Aeon 2. Users can choose cryptocurrency (BTC, ETH, USDT, etc.) to pay. 3. The system calculates the cryptocurrency amount based on the current USD exchange rate of the package. 4. The system generates an address or QR code for users to pay via QR or copy the link to the receiving wallet address 3. After successful payment, players will receive a successful purchase notification and 800 tickets and 500x profit/hr will be added to the ticket wallet and total coin. 4. A successful transaction notification must be sent to the system and the item issuance is completed.