## Phase 1 - requirement change
# | Features
| Epic | Story | Task | Request Date | PIC | Priority | Estimation | Status | Completion Date | Commit ID | Note
1 | GNB | Update UI | Re-design GNB's UI |  | Hue - Des | 0 | 6 | Done
|  |  | Update UI for new design |  | Hùng - FE | 0 | 8 | Done
2 | Wheel | Update UI | Change Wheel Background |  | Hue - Des | 0 | 6 | Done
[6 empty] | 0 | 32
2 | Earn | Update UI | Re-design popups for quest flow | Aug 28 | My - BA |  |  | Done
|  |  | Update new flow and popups' design of the quest | Aug 28 | Hoàng - FE |  |  | Done
|  | Add quest | Add 3 new quests "Post on X", Like on X", "Comment on X" | Aug 29 | Hoàng - BE |  |  | Done
|  |  | Change waiting time from 30m to 10s | Sep 6 | Hoàng - FE |  |  | Done
|  |  | Add timer to Checking button | Sep 10 | Hùng - FE | 0 | 40 | Done
|  | Fix bugs quest "Post on X" | Every time the user clicks on the action button, it will navigate to a different content to post | 10 Sep |  |  |  | To-do |  |  | Khách yêu cầu tạm xóa, đợi tìm ra cách đổi được nhiều content thì sẽ update lại
| Analytics | Google Analytic | Add custon event to track retention rate. | Sep 4 | Hùng - FE | 0 | 18 | Done | Sep 9
| Friend | Friend referrals | Referral point adjustment |  | Hoàng - BE | 1 | 24 | Done
|  |  | Create 100 dumy referral code | Aug 30 | Hoàng - BE | 1 | 26 | Done | Aug 30
4
| Monitor Webhook to Discord |  |  |  | Hoàng - BE |  |  | To-do | done 2/4 on Sep 10 |  | tạm disable
5 | Database | Add column on DB | 1. first name, last name, username |  | Hoàng - BE |  |  | Done
|  |  | 2. createAt for event tracking |  | Hoàng - BE |  |  | Done
|  |  | 3. wallet address info |  | Hoàng - BE |  |  | Done
|  |  | 4. referrerID/refereeCount/premiumRefereeCount |  | Hoàng - BE |  |  | Done
| Telegram Bot | Config the bot | Insert QR for the bot and add space | Sep 11 | Hùng - FE |  |  | Done | Sep 11