## Phase 2 - timeline
[7 empty] | Release 1 |  | Release 2
Plan Timeline |  |  |  | 2024-09-16 | 2024-09-23 |  | 2024-09-30 |  | 2024-10-07 |  | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 |  | 2024-11-11 | 2024-11-18 |  | 2024-11-25 |  | 2024-12-02
Phase | Task | Subtask | PIC | Week1 | Week2 |  | Week3 |  | Week4 |  | Week5 | Week6 | Week7 | Week8 |  | Week9 | Week10 |  | Week11 |  | Week12
2.1 | In-App Purchase |  | Hoang |  | dev done | test | UAT | fix bugs if needed | deploy prod | test prod + monitoring
| Onchain Claim by Ton Space |  | Hung |  |  |  | test + UAT | fix bugs if needed | deploy prod | test prod + monitoring
| Admin Portal | Login | Nam Huy |  | test | UAT | deploy prod | test prod + monitoring
|  | Role-Based Access Control | Nam Huy |  | test | UAT | deploy prod | test prod + monitoring
|  | View database | Nam Huy |  |  |  | test | UAT | deploy prod | test prod + monitoring
|  | Out-link quest | Huy + Tuan |  |  |  | test | UAT | deploy prod | test prod + monitoring
|  | Main Banner (both Admin and App) | Huy + Tuan |  |  |  | test | UAT | deploy prod | test prod + monitoring
After 10/10
2.2 |  | Special Events | Hoang+ Tuan | [9 empty] | test + UAT/ deploy | deploy prod | test prod + monitoring
|  | Daily Quests - Invest, tap, post quest | Huy + Tuan | [9 empty] | test + UAT | deploy prod | test prod + monitoring
|  | In-App Purchase | Hoang + Tuan | [11 empty] | test + UAT | deploy prod | test prod + monitoring
|  | Coupon System | Hoang + Tuan | [13 empty] | test + UAT | deploy prod | test prod + monitoring
| Special Event (on App) |  | Hoang + Tuan | [13 empty] | test + UAT | deploy prod | test prod + monitoring
| Coupon System (on App and Admin) |  | Hoang + Tuan | [9 empty] | start 10/31 | dev done + test 11/5 | fix bug + deploy from 11/6 |  |  |  | test + UAT | deploy prod | test prod + monitoring
| Airdrop Popup (on App) |  | Hoang | [7 empty] | dev done + test + deploy | done
| AdsGram Integration |  | Hoang | [8 empty] | dev done + test on 10/22 - deploy on 10/23 | done
| Aeon Integration |  | Hoang | [8 empty] | from 10/23 | dev done + test on 10/30 | deploy to prod on 11/4
| CEX UID input |  | Hoang + Tuan | [10 empty] | start on 11/6 | dev done + test + fix bug on 11/8
| Aidrop point update |  | Hoang +Tuan | [10 empty] | start on 11/7